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	Notsi Solar Park (475 MW) Request for Quotation (RFQ)
	Doc No.
	NSI-00-PR-QUO-001

	
	
	Rev. No.
	00

	
	
	Rev. Date
	05/05/2026






	Date:
	15 April 2026
	
	RFQ Reference Number:
	CNWE-SH-RFQ-2026-30




You are hereby invited to tender for the below mentioned Scope of Work / Supply, in accordance with the Project Specifications and Requirements as specified.



	Project Details:
	

	Project Name:
	Notsi 475MW Solar Park

	Contract No:
	

	Location:
	Dealesville, Freestate, Tokologo Municipality

	Completion Date:
	15 May 2028





	RFQ Specific Details:
	

	Scope of Work/Supply:
	The appointed contractor shall procure and construct the site temporary facilities for the NOTSI PV Project.
The contractor must tender for temporary construction works, including preliminaries, main construction works, HVAC installation, water heater installation, warranty support and post-completion maintenance services.
All prices shall be tax-inclusive and quoted in South African Rand (R). The contractor must quote item by item, including unit price and total price for each item listed below. All prices must be comprehensive unit prices.
The total construction period shall not exceed 120 calendar days. The contractor must state the expected duration for each item clearly and propose payment milestones and percentages for negotiation.

1. Equipment to be Tendered On
1.Bill No. 1 - Preliminaries
	No.
	Description
	Unit
	Quantity
	Requirements

	1.1
	Fixed Costs
	Lump Sum
	1
	Including one-off inputs such as on-site facility erection and temporary works

	1.2
	Duration-Related Costs
	Month
	4
	-

	1.3
	Safety Measures Costs
	Lump Sum
	1
	Included in the comprehensive unit price



2. Bill No. 2 - Main Construction
	No.
	Description
	Unit
	Quantity
	Requirements

	2.1
	Steel Gate, 6m × 1.8m high
	Set
	3
	Supply and installation

	2.2
	Steel Gate, 3m × 1.8m high
	Set
	1
	Supply and installation

	2.3
	Wire mesh gate, 8m × 2.0m high with anti-theft barbed wire on top (for storage yard)
	Set
	2
	Supply and installation

	2.4
	Wire mesh gate, 4m × 1.8m high (for office area)
	Set
	2
	Supply and installation

	2.5
	Galvanized AZ275 aluminum-zinc roof sheet 0.4mm thick; columns: 80×4mm galvanized steel pipe; rails: 50×3.5mm galvanized steel pipe; top rail: 30×3mm galvanized steel pipe; diagonal braces: 30×3mm galvanized steel pipe. Fence height: 3m above ground. Wall sheets fixed with wire or screws.
	m
	800
	Supply and installation

	2.6
	Internal galvanized diamond mesh fence (mesh size 50/75mm); columns: 80×4mm galvanized steel pipe; rails: 50×3.5mm galvanized steel pipe; top rail: 30×3mm galvanized steel pipe; diagonal braces: 30×3mm galvanized steel pipe. Fence height: 2m above ground, fixed with wire.
	m
	120
	Supply and installation

	2.7
	External galvanized diamond mesh fence (mesh size 50/75mm); columns: 80×4mm galvanized steel pipe; rails: 50×3.5mm galvanized steel pipe; top rail: 30×3mm galvanized steel pipe; diagonal braces: 30×3mm galvanized steel pipe. Fence height: 2.4m above ground, with 0.5m high anti-theft barbed wire on top, tensioned and fixed with wire.
	m
	953
	Supply and installation

	2.8
	Crushed stone placement (19mm particle size) for living quarters, office area and storage yard
	m³
	1,000
	Supply and installation

	2.9
	Earthworks (filling): mainly 500mm platform filling for living quarters and partial indoor backfilling (approx. 500mm thick); maximum layer thickness ≤250mm; soil compaction factor ≥98%.
	m³
	13,000
	Supply and installation

	2.10
	Site clearing and grading (including tree removal)
	m²
	70,800
	-

	2.11
	Kerb installation (H=400×L=700×W=150)
	m
	920
	Supply and installation

	2.12
	Concrete paving bricks 600×600×20mm thick, 1m wide footpath laid in running bond (footpaths only on both sides of main camp roads)
	m
	180
	Supply and installation

	2.13
	Installation of 3 sets stainless steel flagpoles and foundation construction (flagpoles supplied by Client)
	Lump Sum
	1
	Installation and construction

	2.14
	CCTV system for living quarters (including 8 cameras, covering living quarters, cameras with infrared alarm function)
	Set
	1
	Supply and installation

	2.15
	CCTV system for office area (including 7 cameras, covering office area, cameras with infrared alarm function)
	Set
	1
	Supply and installation

	2.16
	CCTV system for storage yard (including 20 cameras, covering storage yard, cameras with infrared alarm function)
	Set
	1
	Supply and installation

	2.17
	200W streetlight, 6m pole, standard South African type (installed on both sides of roads, including lightning protection and street light distribution board)
	Set
	15
	Supply and installation

	2.18
	800W solar streetlight, 5 sets; minimum 4 lamps per set, 10m pole, standard South African type (installed in storage yard, including lightning protection and street light distribution board)
	Set
	5
	Supply and installation

	2.19
	Water pump supply and commissioning (with associated control system)
	Unit
	2
	Supply and installation

	2.20
	10m³ PE water storage tank supply and installation
	Unit
	14
	Supply and installation

	2.21
	External water supply pipeline network
	m
	1,143
	Supply and installation

	2.22
	External drainage pipeline network
	m
	935
	Supply and installation

	2.23
	External stormwater drainage network (including 12 brick stormwater manholes)
	m
	248
	Supply and installation

	2.24
	Concrete works (C15 floor, C30 safe house, C30 structural foundation, etc.)
	m³
	572
	Supply and installation

	2.25
	Red brick road and floor construction
	m²
	3,420
	Supply and installation

	2.26
	Concrete road (C25)
	m³
	342
	Supply and installation

	2.27
	Diesel generator, 300KVA
	Unit
	2
	Supply and installation

	2.28
	Diesel generator, 200KVA
	Unit
	2
	Supply and installation

	2.29
	Diesel generator, 50KVA
	Unit
	1
	Supply and installation

	2.30
	12m³ diesel storage tank (including installation and all permits for refueling, storage and usage)
	Set
	1
	Supply and installation

	2.31
	3m³ diesel storage tank (including installation and all permits for refueling, storage and usage)
	Set
	1
	Supply and installation

	2.32
	External power supply systems (including cable laying, connection from buildings to generators or other equipment, cable connection, distribution board installation (distribution board supplied by Client), control cabinet connection, etc.)
	m
	1,865
	Supply and installation

	2.33
	Cable trench (including excavation, backfilling, site cleaning and related works)
	m
	750
	Construction

	2.34
	Container house installation (including all associated works: internal water and electricity, sanitary ware, furniture, decoration, structure, etc.)
	Lump Sum
	1
	Installation and construction

	2.35
	Steel structure installation (including all associated works: internal water and electricity, sanitary ware, furniture, decoration, structure, etc.)
	T
	54.6
	Installation and construction



3. Bill No. 3 - HVAC System
	No.
	Description
	Unit
	Quantity
	Requirements

	3.1
	Wall-Mounted Air Conditioner Installation (cooling/heating type) including piping, brackets and commissioning
	Unit
	232
	Installation only



4. Bill No. 4 - Water Heater
	No.
	Description
	Unit
	Quantity
	Requirements

	4.1
	40L Electric Water Heater Installation (including piping connection and earth leakage protection)
	Unit
	134
	Installation only




5. Bill No. 5 - Post-Completion Works
	No.
	Description
	Unit
	Quantity
	Requirements

	5.1
	1-Year Project Warranty: Warranty period is 12 months from acceptance / handover. Free repair of defective structures, finishes, etc.; bear all costs for labour, transport, spare parts, etc.; respond within 24 hours of fault notification and attend / complete repair within agreed time.
	Year
	1
	Warranty support

	5.2
	After the 1-year warranty expires, the project automatically enters a paid post-warranty maintenance phase. A separate maintenance agreement may be signed or service provided on an ad-hoc basis. Maintenance services, labour travel and spare parts replacement to be settled at cost price or preferential negotiated price. A clear quotation list shall be provided for confirmation before execution.
	Year
	2
	Paid maintenance support



6. Quotation Requirements
· Quotation Format: Quote unit price and total price for each item listed above. All prices must be comprehensive unit prices.
· Quotation Validity: Quotation shall remain valid for at least 90 days from the date of submission.
· Project Duration: State the expected duration for each item clearly. Total construction period shall not exceed 120 calendar days.
· Payment Terms: Please propose suggested payment milestones and percentages. CNWE reserves the right to negotiate.

7. Other Conditions
· CNWE reserves the right to negotiate, reject all quotations or cancel this procurement without any liability.
· Submission of a quotation shall be deemed acceptance of all terms and conditions in this RFQ.
· All work must comply with applicable South African laws, site HSE requirements, project specifications and relevant construction standards.
· The contractor must provide all labour, equipment, plant, materials, supervision, transportation, permits, testing, commissioning and documentation necessary to complete the works unless clearly stated otherwise.

RFQ Specific Requirements: Duration of activity: Total construction period shall not exceed 120 calendar days.

Start date: To be confirmed
	Quantity
	Type
	Additional specifications

	1
	Temporary facilities construction package
	Procurement and construction of temporary construction works for the NOTSI PV Project, including preliminaries and all Bill No. 1 to Bill No. 5 items.

	1
	Main construction works
	Gates, fencing, crushed stone, earthworks, clearing, kerbs, paving, CCTV, lighting, pumps, tanks, water supply, drainage, stormwater, concrete works, roads, generators, diesel tanks, electrical works, cable trenches, container houses, steel structures, PV and energy storage.

	1
	Mechanical and electrical installation
	HVAC installations, water heater installations, power supply connections, commissioning and related controls as specified.

	1
	Warranty and maintenance support
	One-year warranty from acceptance / handover and two-year paid post-warranty maintenance support as specified.


Terms & Conditions: As per CNWE service agreement contract and the quotation requirements stated in this RFQ.

8. Project Requirement
All fire prevention and firefighting equipment must be suitable for construction site conditions, PV project activities, hot work, fuel storage, chemical storage, temporary offices, laydown areas, plant areas and emergency response requirements.
All equipment and service records must be suitable for audit purposes and for inclusion in the project HSE file.


	Form of Agreement:
	Service provider / contractor

	Validity of Quote:
	90 days from date of submission

	Delivery:
	As per agreement

	BOQ:
	As Project BOQ

	Specifications:
	As per scope of work

	Drawings:
	As per project drawings where applicable

	RFQ Submission Date:
	Date:      25 May 2026               Time: 16h00

	Submission of Quote:
	By mail: johan@cggcpower.com
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RFQ Specific Requirements:
Duration of activity: Duration of Project Start date:


Service required:
	Quantity
	Type
	Additional specifications

	       
	
	


	
	
	



Terms & Conditions: As per CNWE service agreement contract.
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CNWE Procurement Process & Requirements:

All RFQ’s to be submitted to CRM Office for processing
Procurement of all services will be based on a commercial basis.
Only contractors & SMME’s which have been fully vetted by CRM will be considered.

	Returnable to be submitted (Check List)

	
Quotation / Proposal Including Cover Letter
	

	BEE Certificate / WBHO Affidavit
	

	Certified copy of roadworthy certificate and licence disc
	

	Certified training certificates/competencies of operators
	

	
Service record of plant
	

	
Tax clearance document
	

	
Proof of insurance and ownership
	

	
Vat Registration
	

	
Letter of Good Standing
	

	
Company registration document
	

	
Proof of Address
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