## Milestones
Implementation Schedule of Installation for PV areas in Notsi PV Project
Activity ID | Activity Name | Original Duration | Start | Finish
光伏区一标段 PV Area Section 1 |  | 515 | 2026-04-15 | 2027-08-13
场地基础工程 Site Foundation Engineering |  | 231 | 2026-06-13 | 2027-01-17
桩基工程 Pile Foundation Engineering |  | 231 | 2026-06-13 | 2027-01-17
A6650 | 钻孔质量验收 Drilling Quality Acceptance | 90 | 2026-10-01 | 2026-12-25
立桩施工 Pile Installation |  | 113 | 2026-10-02 | 2027-01-17
支架及附属结构安装 Bracket and Auxiliary Structure Installation |  | 106 | 2026-10-15 | 2027-01-23
A7110 | 传动轴安装Drive shaft installation | 100 | 2026-10-21 | 2027-01-23
光伏组件安装 PV Module Installation |  | 107 | 2026-10-26 | 2027-02-03
A6910 | 组件外观与电气连接验收 Module Appearance and Electrical Connection Acceptance | 100 | 2026-11-01 | 2027-02-03
汇流箱安装 Combiner Box Installation |  | 155 | 2026-10-04 | 2027-02-27
A6970 | 通电前检查 Pre-energization Inspection | 15 | 2027-02-13 | 2027-02-27
中低压电缆敷设 Medium and Low Voltage Cable Installation |  | 353 | 2026-08-17 | 2027-07-16
A7100 | 电缆沟回填 Cable Trench Backfilling | 180 | 2027-01-27 | 2027-07-16
气象站安装 Weather Station Installation |  | 37 | 2026-12-23 | 2027-01-27
A7220 | 气象站校准 Weather Station Calibration | 5 | 2027-01-22 | 2027-01-27
防雷与接地系统施工 Lightning Protection and Earthing System Construction |  | 328 | 2026-08-17 | 2027-06-22
A7320 | 接地电阻测试 Earthing Resistance Testing | 15 | 2027-06-08 | 2027-06-22
单体调试 Single Unit Commissioning |  | 211 | 2027-01-27 | 2027-08-13
A7380 | 气象站调试 Weather Station Commissioning | 15 | 2027-01-27 | 2027-02-10
A7340 | 光伏组件及支架单体调试 PV Module Single Unit Commissioning | 60 | 2027-02-03 | 2027-04-01
A7360 | 箱逆变一体机调试 Containerized Inverter Commissioning | 60 | 2027-06-18 | 2027-08-13
Remark：1.The specific schedule may be adjusted according to the updated schedule agreed by both Parties. 2.Particularly, the start time may be adjusted to the end of June once agreed by both Parties,but the completion time of this project shall not be late than 13th,August,2027.
Note on D4: Louis Liu: This time could be adjusted

## L3 (hidden)
Activity ID | Activity Name | Original Duration | Start | Finish
光伏场区部分 Photovoltaic site area |  | 515 | 2026-04-15 | 2027-08-13 | L3
光伏区一标段 PV Area Section 1 |  | 515 | 2026-04-15 | 2027-08-13 | L3
商务阶段 Business phase |  | 34 | 2026-04-15 | 2026-05-27 | L3
A6450 | 询源 Sourcing Inquiry | 10 | 2026-04-15 | 2026-04-24 | L3
A6460 | 商务、技术、价格、工期谈判 Negotiations on business, technology, price and construction period | 15 | 2026-04-24 | 2026-05-08 | L3
A6470 | 合同签订Contract Signing | 5 | 2026-05-09 | 2026-05-13 | L3
A6480 | NTP | 3 | 2026-05-25 | 2026-05-27 | L3
施工准备阶段 Construction Preparation Stage |  | 32 | 2026-05-14 | 2026-06-13 | L3
A6490 | 施工人员安全培训与技术交底 Construction Personnel Safety Training and Technical Disclosure | 2 | 2026-05-14 | 2026-05-16 | L3
A6500 | 施工场地围挡搭建与安全警示布置 Construction Site Enclosure Erection and Safety Warning Layout | 5 | 2026-05-16 | 2026-05-21 | L3
A6510 | 施工临时设施搭建 Temporary Construction Facility Establishment | 5 | 2026-05-16 | 2026-05-21 | L3
A6530 | 施工图纸会审与技术交底Construction Drawing Review and Technical Disclosure | 3 | 2026-06-06 | 2026-06-08 | L3
A6540 | 表层杂物、植被清理 Surface Debris and Vegetation Clearance | 5 | 2026-06-08 | 2026-06-13 | L3
场地基础工程 Site Foundation Engineering |  | 231 | 2026-06-13 | 2027-01-17 | L3
桩基工程 Pile Foundation Engineering |  | 231 | 2026-06-13 | 2027-01-17 | L3
A6560 | 测量放线 Surveying and Setting Out | 5 | 2026-06-13 | 2026-06-18 | L3
桩基钻孔 Pile Drilling |  | 97 | 2026-09-25 | 2026-12-25 | L3
A6610 | 布桩/钻孔机定位及作业 Drilling Rig Positioning | 90 | 2026-09-25 | 2026-12-18 | L3
A6630 | 孔壁清理与垂直度检测 Hole Wall Cleaning and Verticality Detection | 90 | 2026-09-29 | 2026-12-23 | L3
A6640 | 孔底沉渣清理 Hole Bottom Sediment Cleaning | 90 | 2026-09-29 | 2026-12-23 | L3
A6650 | 钻孔质量验收 Drilling Quality Acceptance | 90 | 2026-10-01 | 2026-12-25 | L3
立桩施工 Pile Installation |  | 113 | 2026-10-02 | 2027-01-17 | L3
A6670 | 桩体吊装就位 Pile Hoisting and Positioning | 94 | 2026-10-02 | 2026-12-30 | L3
A6680 | 桩体垂直度校正 Pile Verticality Correction | 94 | 2026-10-02 | 2026-12-30 | L3
A6690 | 混凝土浇筑 Concrete Pouring | 99 | 2026-10-02 | 2027-01-03 | L3
A6700 | 养护作业 Curing Operation | 99 | 2026-10-09 | 2027-01-10 | L3
A6710 | 桩拉拔检测 Pile Bearing Capacity Testing | 106 | 2026-10-09 | 2027-01-17 | L3
支架及附属结构安装 Bracket and Auxiliary Structure Installation |  | 106 | 2026-10-15 | 2027-01-23 | L3
A6720 | 驱动底座安装与调平Installation and Leveling of Drive Base | 100 | 2026-10-15 | 2027-01-17 | L3
A6740 | 回转驱动 / 从动驱动安装Installation of Slewing Drive and Driven Drive | 100 | 2026-10-15 | 2027-01-17 | L3
A6750 | 檩条预装Purlin pre-installation | 100 | 2026-10-15 | 2027-01-17 | L3
A6760 | 扭矩管安装Torque tube installation | 100 | 2026-10-15 | 2027-01-17 | L3
A6770 | 檩条定位排布Positioning and layout of purlins | 100 | 2026-10-15 | 2027-01-17 | L3
A6780 | 统一最终紧固Final Unified Tightening | 100 | 2026-10-15 | 2027-01-17 | L3
A7110 | 传动轴安装Drive shaft installation | 100 | 2026-10-21 | 2027-01-23 | L3
光伏组件安装 PV Module Installation |  | 107 | 2026-10-26 | 2027-02-03 | L3
A6870 | 组件安装 Module Hoisting and Positioning | 100 | 2026-10-26 | 2027-01-28 | L3
A6880 | 组件固定 Module Fixing | 100 | 2026-10-26 | 2027-01-28 | L3
A6890 | 组件串接 Module String Connection | 100 | 2026-10-26 | 2027-01-28 | L3
A6900 | 组件平整度调整 Module Flatness Adjustment | 100 | 2026-10-26 | 2027-01-28 | L3
A6910 | 组件外观与电气连接验收 Module Appearance and Electrical Connection Acceptance | 100 | 2026-11-01 | 2027-02-03 | L3
电气设备建安施工 Electrical Equipment Construction and Installation |  | 353 | 2026-08-17 | 2027-07-16 | L3
汇流箱安装 Combiner Box Installation |  | 155 | 2026-10-04 | 2027-02-27 | L3
A6920 | 汇流箱基础施工Oundation Pouring | 30 | 2026-10-04 | 2026-11-01 | L3
A6930 | 汇流箱钢结构及汇流箱安装 Combiner Box installation | 45 | 2026-10-21 | 2026-12-02 | L3
A6940 | 汇流箱接线 Combiner Box Wiring | 45 | 2027-01-02 | 2027-02-13 | L3
A6950 | 箱体接地 Box Earthing | 45 | 2027-01-02 | 2027-02-13 | L3
A6970 | 通电前检查 Pre-energization Inspection | 15 | 2027-02-13 | 2027-02-27 | L3
箱逆变一体机安装 Containerized Inverter Installation |  | 273 | 2026-10-04 | 2027-06-18 | L3
A6980 | 设备基础施工 Equipment Foundation Pouring | 85 | 2026-10-04 | 2026-12-23 | L3
A6990 | 设备吊装就位 Equipment Hoisting and Positioning | 63 | 2026-11-27 | 2027-01-25 | L3
A7010 | 高低压电缆接线 High and Low Voltage Cable Wiring | 63 | 2027-04-13 | 2027-06-11 | L3
A7030 | 箱体接地与防雷连接 Box Earthing and Lightning Protection Connection | 63 | 2027-04-13 | 2027-06-11 | L3
A7040 | 设备外观与接线验收 Equipment Appearance and Wiring Acceptance | 7 | 2027-06-11 | 2027-06-18 | L3
中低压电缆敷设 Medium and Low Voltage Cable Installation |  | 353 | 2026-08-17 | 2027-07-16 | L3
A7050 | 电缆沟开挖 Cable Trench Excavation | 260 | 2026-08-17 | 2027-04-19 | L3
A7070 | 电缆敷设 Cable Installation | 260 | 2026-10-07 | 2027-06-08 | L3
A7080 | 电缆固定 Cable Fixing | 200 | 2026-12-02 | 2027-06-08 | L3
A7090 | 电缆接头制作 Cable Joint Fabrication | 180 | 2026-12-30 | 2027-06-18 | L3
A7095 | 电缆绝缘测试 Cable Insulation Testing | 180 | 2027-01-13 | 2027-07-02 | L3
A7100 | 电缆沟回填 Cable Trench Backfilling | 180 | 2027-01-27 | 2027-07-16 | L3
气象站安装 Weather Station Installation |  | 37 | 2026-12-23 | 2027-01-27 | L3
A7169 | 气象站基础Weather station foundation | 15 | 2026-12-23 | 2027-01-06 | L3
A7170 | 气象站支架安装 Weather Station Bracket Installation | 7 | 2027-01-06 | 2027-01-13 | L3
A7180 | 传感器安装 Sensor Installation | 5 | 2027-01-13 | 2027-01-17 | L3
A7190 | 数据采集器安装 Data Logger Installation | 5 | 2027-01-13 | 2027-01-17 | L3
A7200 | 通信模块安装 Communication Module Installation | 5 | 2027-01-13 | 2027-01-17 | L3
A7210 | 供电线路连接 Power Supply Line Connection | 5 | 2027-01-18 | 2027-01-22 | L3
A7220 | 气象站校准 Weather Station Calibration | 5 | 2027-01-22 | 2027-01-27 | L3
照明设备安装 Lighting Equipment Installation |  | 120 | 2026-10-04 | 2027-01-25 | L3
A7230 | 照明基础施工Lamps foundation construction | 85 | 2026-10-04 | 2026-12-23 | L3
A7240 | 灯具安装 Lamps Installation | 30 | 2026-12-23 | 2027-01-20 | L3
A7270 | 照明测试 Lighting Test | 5 | 2027-01-20 | 2027-01-25 | L3
防雷与接地系统施工 Lightning Protection and Earthing System Construction |  | 328 | 2026-08-17 | 2027-06-22 | L3
A7280 | 开挖 Excavation | 260 | 2026-08-17 | 2027-04-19 | L3
A7290 | 接地网敷设 Earthing Grid Layout | 200 | 2026-12-02 | 2027-06-08 | L3
A7330 | 回填Back filling | 200 | 2026-12-02 | 2027-06-08 | L3
A7320 | 接地电阻测试 Earthing Resistance Testing | 15 | 2027-06-08 | 2027-06-22 | L3
单体调试 Single Unit Commissioning |  | 211 | 2027-01-27 | 2027-08-13 | L3
A7380 | 气象站调试 Weather Station Commissioning | 15 | 2027-01-27 | 2027-02-10 | L3
A7340 | 光伏组件及支架单体调试 PV Module Single Unit Commissioning | 60 | 2027-02-03 | 2027-04-01 | L3
A7360 | 箱逆变一体机调试 Containerized Inverter Commissioning | 60 | 2027-06-18 | 2027-08-13 | L3