## Sheet1
Delivery Plan of Plant，Equipment and Materials for Notsi PV Project
No. | Name | Expected Arrival Time | Workscope
1 | PV module | 2025.10-2027.2 | heavy and voluminous cargoes shall be unloaded and storage by Party B
2 | Solar Tracker(mounting structure) | 2026.7-10 | heavy and voluminous cargoes shall be unloaded and storage by Party B;Component and comaccessory parts could be unloaded and storage by Party A
3 | Integrated Transformer & Inverter Station | 2026.11 | heavy and voluminous cargoes shall be unloaded and storage by Party B;Component and comaccessory parts could be unloaded and storage by Party A
4 | Combiner Box | 2026.12 | heavy and voluminous cargoes shall be unloaded and storage by Party B;Component and comaccessory parts could be unloaded and storage by Party A
5 | 132KV Transformer | 2027.6 | heavy and voluminous cargoes shall be unloaded and storage by Party B
6 | PV Cable | 2026.7-10 | heavy and voluminous cargoes shall be unloaded and storage by Party B
7 | Low Voltage DC Cable | 2026.7-10 | heavy and voluminous cargoes shall be unloaded and storage by Party B
8 | Optical Fiber between Combiner Box and Inverter | 2026.1 | unloading and storage by Party A
Remark: For more detailed information ,refer to BOQ