APPENDIX I – Documents to be delivered

1. 	General

1.1 	This appendix sets out the minimum scope of information, documents, and drawings, to be

submitted by the Subcontractor to the Contractor after the signature date of this Subcontract. The Subcontractor shall submit all information, drawings and documents.

1.2 	The Subcontractor shall provide the Contractor in such number of copies as may be indicated by the

Contract  (including soft and hard copies) with all the information and documentation detailed hereby and in the Subcontract. Editable format of any Document shall be provided upon Contractor’s request.

1.3 	Except otherwise agreed by the Parties, all submissions shall be done through the Project

Communication and Data Management System as specified in the OTS along with a transmittal sheet.

1.4 	The Contractor and/or the Contract's Representatives shall be responsible for reviewing all the

Subcontractor's Documents for compliance with the Subcontract and Good Utility Practice.

1.5 	The description and specifications of the electrical protective devices to be incorporated in the Plant in order to protect the Transmission System (as such term is defined in the PPA) are of particular importance and require the coordination and approval of the Employer and Grid prior to incorporation into the design of the Plant.

1.6 	  For the avoidance of doubt and regardless of what is otherwise set out in the Subcontract, to the extent the Subcontractor is submitting a Document which is to be then submitted by the Contractor to the Employer under the PPA the time frame for the Subcontractor to submit that Document will be the earlier of (i) the time frame set out in the Subcontract and (ii) ten (10) Business Days less than the time period that the Contractor has to submit such Document to the Employer under the main EPC contract.

2. 	Documents to be delivered on the signature date of this Subcontract

2.1 	The Subcontractor shall submit the following Documents to the Contractor on the signature date of   this Subcontract:

2.1.1 	All drawings(where applicable) and documents required for permitting, certifying and/or licensing of the Facility, and copies of all official correspondence between Subcontractor and Governmental Authorities with jurisdiction over the same;

2.1.2 	General arrangement and layout drawings, including laydown areas and Site office

areas;

2.1.3 	Level 2 Schedule (both in Primavera P6 Professional and pdf format) which meets

the requirements of the Subcontractor and the Contractor ;

2.1.4 	All requested documents, data, drawings, lists, etc. related to the technical

Requirements which is under subcontractor’s work scope.

3. 	Documents to be delivered after the signature date of this Subcontract

3.1 	The Subcontractor shall submit the following Documents to the Contractor not later than thirty (30)Days after the signature date of this Subcontract:

3.1.1       Functional and organizational structure  and communication matrix;

3.1.2 	 All Project plans according to the Quality Assurance Plan in accordance with this      Subcontract;

3.1.3 	The HSSE Management Plan, prepared in accordance with the requirements of

Appendix Z (Subcontractor Management HSSE Standard) and procedures and test specifications related to all environmental investigations, surveys and monitoring undertakings, as well as relevant test results promptly after their completion;

3.1.4 	A master list of engineering document deliverable  with target submission dates              for each document (the “Engineering Master Document List”). Such list shall be prepared in accordance with this Subcontract and Good Utility Practice and include:

3.1.4.1 	Clear differentiation by discipline (civil, structural, mechanical,

electrical, instrumentation and control, auxiliary facilities, etc.);

3.1.4.2 	Clear differentiation between priority 1 and priority 2 submissions

proposed, subject to Contractor’s approval;

3.1.5 	The updated list of Subcontractors and Major Equipment suppliers, the manpower

mobilization forecast and the template of weekly construction production control and forecasting for Construction works and other critical activities as required by the subcontract.

3.2 	The Subcontractor shall submit the following Documents to the Contractor by the dates set forth below or,if date is not specified, as and when each such Document is required by the Contractor:

3.2.1 	Level 4 Baseline schedule shall be issued within the first 10 days after NTP date. The L4 Plan includes, but is not limited to, relevant information on the quantity and parameters of input such as construction progress, manpower, machinery, tools and appliances for the project.

3.2.2      Not later than fifteen (15) Days prior to the start date of Site activities of each of  the Subcontractors, full and detailed copies of the organizational chart for each Subcontractor’s personnel working on the Project inclusive of all names appointed to designated positions;

3.2.3 	 Site test reports and reports of any relevant studies that are necessary to be carried out by the Subcontractor in due time after issuance thereof and in any case not later than the start of the Tests on completion;

4.   Documentation

4.1   General

4.1.1 	The Subcontractor shall be responsible for submitting all Documents to the Contractor on a schedule consistent with Appendix B (Implementation Schedule ). The Subcontractor shall be responsible for submitting all Documents to be prepared by it for review/approval by the Contractor that provide enough time for the Contractor to check, assess and comment upon the Documents within a reasonable time, which shall not be less than fourteen (14) Working Days and for documents that shall be submitted to the Employer for review/approval should be not less than twenty (20) working days. Such submissions shall be to a standard in line with good industry practice and at such a time as to permit the Subcontractor to fulfil the obligations of the Schedule/Program. The Contractor shall use its reasonable efforts to complete such activities.

4.1.2 	The Subcontractor is reminded that neither the submission of any Document nor its

review, nor the making of comments or the raising of queries thereon, nor suggestions or recommendations on the same by the Contractor (or the O&M Subcontractor through the Contract) shall prejudice or affect any of the Subcontractor's obligations under the Subcontract and the Subcontractor shall check and verify that any such comments or queries, suggestions and recommendations are proper and correct and shall not give rise to a breach of the Subcontract before acting on them and any review or approval shall not excuse the Subcontractor from design liability(if any) and other responsibilities under the Subcontract.

4.1.3 	The quality of all Documents submitted by the Subcontractor shall conform to Good

Utility Practice and acceptable international practice and be in English language.

4.1.4 	With regard to the interconnection of the Facility to facilities built by others, the drawings and descriptions included in Appendix A (Contract's Technical Specifications) shall be deemed to be indicative only.

4.1.5 	Subcontractor shall provide to Contractor such reasonable assistance, documentation

and/or information as Contractor may request in order to obtain the Approvals as specified as being Contractor’s responsibility).

4.2 	Documentation Review Procedure

4.2.1 	Any review by the Contractor shall not relieve the Subcontractor of its obligations under the Subcontract.

4.2.2 	When submitting Documents for review, including any prepared by a Subcontractor,

the Subcontractor shall certify in each case that it has examined such Documents and that they comply with the requirements of the Subcontract.

4.2.3 	Except as otherwise provided in the Subcontract, within the relevant period stated  in paragraph 4.1, the Contractor shall either:

4.2.3.1 	return to the Subcontractor one (1) copy of any Documents submitted to

the Contractor with no comments or queries endorsed thereon;

4.2.3.2 	return one (1) such copy including any comments or queries which it

may have endorsed thereon; or

4.2.3.3 	return one (1) such copy with rejected status including any comments

or queries which it may have endorsed thereon.

A Document comments review sheet (into an agreed format) shall be issued to facilitate rapid transfer of any comments or queries.

4.2.5 	If the Contractor fails to take any such action within the relevant period stated in

paragraph 4.1, then the Documents shall be deemed to have been returned to the Subcontractor with no comments or queries endorsed thereon.

4.2.6 	The Subcontractor shall, within five (5) Working Days of receipt of any comments or

queries on any Documents amend such Documents in order to implement and accommodate the Contract's comments or queries and resubmit such Documents for review as above, except that the period for review of resubmitted Documents by the Contractor shall be seven (7) Calendar Days. If the Document was rejected, then the normal review period in accordance with paragraph 4.1 shall apply.

5. 	Final Records and As-Built Drawings

5.1 	The Subcontractor shall provide the final records for the Facility and shall include test results of the tests performed, all reflecting as-built conditions, as well as certificates attesting the  condition of the Materials and Equipment provided by the Subcontractor under the Subcontract.

5.2 	 All final records shall be in the English language and kept as hard copies (and soft copies where available).

6. 	Conflict

6.1 	Notwithstanding anything else contained in this appendix, in the event of any conflict between

the provisions/content of this appendix and the provisions/content of the main body of the Subcontract, the provisions/content of the main body of the Subcontractor shall prevail and over-ride

Annex 1 – Subcontractor Communication Forms

Required submission by the Subcontractor

| Document |  | Format | Submission date | SubContractor | Modification |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | response time | time |
| 1 |  |  |  |  |  |
| 2 |  |  |  |  |  |