## Schedule and Milestone
No. | Item | Days | Start/NTP+ Days | Finish/NTP+Days
1 | Foundation | 55 | 0 | 55
2 | Main Structure | 82 | 55 | 137
3 | Decoration | 90 | 137 | 227
4 | Installation | 50 | 227 | 277
5 | Commissioning-O&M Building | 10 | 277 | 287