Appendix E：Liquidated Damages for Delay and Performance

| NO. | Activity Description | Liquidated damages |
| --- | --- | --- |
| 1 | Liquidated damages per day of delay in respect of failure to completion date of Construction and Installation Works for PV Area and approved by Contractor . | 1.5‰(Fifteen per ten thousand) of the total price signed in the contract per day |
| 2 | The Contractor fails to pass the performance test and thus assumed default liability under the Main Contract for reasons attributable to the Subcontractor. | The Subcontractor shall compensate the Contractor for 120% of its Losses under the Main Contract. |
| Maximum Amount of Liquidated Damages: The maximum amount of liquidated damages payable under clause 17.3 (Delay Damages), clause 17.4 (Performance Damages) and clause 17.5 (Other Damages) shall not exceed [Twenty five percent (25%)] of the Subcontract Price. |  |  |