## Sheet1
Division of Work工作划分表
序号No. | 内容及要求 content and requirement | Contractor (Party A) | Subcontractor (Party B)
1 | field offices for both Parties双方现场办公室
1.1 | The office and office equipment and office supplies used by Party A 甲方使用的办公室及办公设备、办公用品 | √
1.2 | The office and office equipment and office supplies used by Party B 乙方使用的办公室及办公设备、办公用品 |  | √
1.3 | Party A provide the area for field office construction by Party B 甲方提供场地，供乙方修建办公室 | √ | √
2 | Site delivery and stock dump 场地交付及堆场
2.1 | construction site and yard 施工场地 | √
2.1.1 | soil yards, material yards, rock yards,storage site土石堆场/材料场地 /仓储场地 | √
2.1.2 | soil and rock dumping sites 弃土石场地 | √
2.1.3 | garbage and waste dumping sites and other sites requred by Party B 弃废物场地和其他乙方需要的场地 |  | √
2.2 | Site formation and maintenance场地平整及维护 |  | √
2.3 | construction workshop used by Party B (if required)乙方现场施工班房 |  | √
2.4 | Third party certification for welder and scaffolder, measuring instrument calibration焊接、脚手架和测量仪器校准第三方认证 |  | √
2.5 | After Party B finishes using the equipment and materials supplied by Party A on site, no surplus materials shall be discarded arbitrarily. Regardless of whether they have residual value or not, Party B shall report them to Party A for inspection. Those approved by Party A may be disposed of by Party B at its own cost.甲方提供的设备与材料，乙方在现场使用完毕后，剩余物资不得随意丢弃；无论有无残值，乙方需上报甲方查验，经甲方同意的可自行处理，费用乙方承担。 |  | √
2.6 | All kinds of NOC application and approval from the local government (as required / as applicable) for Party B scope of works.各类NOC申请及办理(如有需要） |  | √
2.7 | Building permit application and approval from the local government建筑许可申请及办理 |  | √
3 | Power supply电源供应
3.1 | Power supply shall be borne by Party B, and purchasing electricity lines, distribution box and the equipment in the cabinet, cable and accessories, etc.电源供应由乙方负责，乙方自行采购临时施工用电线路所需要的配电箱及箱内设备、电缆及附件等。 |  | √
3.2 | Party B shall provide a more detailed temporary power supply scheme for general Party A approval. Only the scheme approved by Party A can be used for on-site implementation.乙方应提供更加详细的临时电源方案供甲方审批。只有通过甲方审批的方案，方可用于现场实施。 |  | √
3.3 | Expenses of Construction of electricity fee施工电费 |  | √
4 | Construction water delivery施工用水 |  | √
4.1 | 甲方提供接水点位置，乙方自行储存、运输施工用水。Party A shall designate the water supply connection points（water intake point), and Party B shall be responsible for the storage and transportation of construction water on its own. |  | √
4.2 | Party B shall provide a more detailed provisional water plan for approval by Party A. Only the scheme approved by Party A can be used for on-site implementation.乙方应提供更加详细的临时用水方案供甲方审批。只有通过甲方审批的方案，方可用于现场实施。 |  | √
4.3 | Expenses for construction water.施工用水费用 |  | √
5 | gas 气体
5.1 | All construction gas (if required)所有施工使用的气体（如需要） |  | √
6 | material and equipment材料及设备 |  | √
6.1 | material材料 |  | √
6.1.1 | Material Supplied by Party A, refer to other contract annexs:甲方供应的材料参见合同其他附件
6.1.2 | Party B shall supply the remaining material except the material supplied by Party A除甲供材料外，所有其他材料均由乙方提供 |  | √
6.2 | equipment设备 |  | √
6.2.1 | Distribution box, maintenance box, Distribution Box, lighting in Party B’s construction area and related cost.乙方施工区域的配电箱、检修箱、照明箱、照明及相关费用 |  | √
7 | Construction machinery and tools施工机械与机工具
7.1 | All machinery and Vehicle for carrying out this work shall be provided by Party B, including but not limited to Fuel Generator(s), Crane(s), forklift(s), platform lorry (Lorries), etc.为实施本工程所涉及的一切机械均由乙供。包括但不限于：柴发，吊车，叉车，平板车等。 |  | √
7.2 | All Construction machinery and tools are required for the scope of work.所有机械及机工具 |  | √
7.3 | Daily maintenance and maintenance of construction machinery and tools which provided by Party B in the construction area.施工范围内乙方提供的施工机械及机工具的日常保养和维护。 |  | √
7.4 | Inspection equipment (certificates and other documents available)验收设备（合格证等证件具备） |  | √
8 | Joint acceptance of material goods to site材料货到工地后的联合验收 | √ | √
9 | Handling, transportation and customs clearance of materials.设备材料的装卸、运输及报关
9.1 | Equipment materials supplied by Party B 乙方供应设备材料
9.1.1 | Temporary import and return, custom clearance and bank guarantee for the equipment, machine and tool supplied by Party B乙供设备、机工具清关所涉及的暂进复出及银行保函。 |  | √
9.1.2 | warehouse, load, unload, transportation from the factory to site for the equipment and material supplied by Party B乙方供应设备材料仓库、工厂与现场之间的材料装卸与运输。 |  | √
9.1.3 | Examination or test for equipment and material supplied by Party B乙方供应设备材料送检 |  | √
9.2 | Plant,Equipment &Materials supplied by Party A甲供设备材料
9.2.1 | Heavy and voluminous cargoes shall be unloaded,custody and storage by Party B.The unloading location could be appointed by Party B on construction site or in Party B's warehouse/storage area.大件货物卸货、储存和保管由乙方负责，卸货地点可由乙方指定至施工现场或乙方仓库或存储场地。 |  | √
9.2.2 | Component and comaccessory parts could be unloaded and storage by Party A 甲方负责零配件卸货、储存和保管 | √
9.2.3 | Open the package upon arrival and conduct a count, arrival inspection in the witness of both Parties；Party B shall arrange equipment，tools and workers or labors to complete the arrival inspection .双方共同见证到货开箱、清点和到货验收，乙方安排机械工具工人完成到货验收。 | √ | √
10 | Construction site firefighting layout 现场消防
10.1 | Temporary mobile fire fighting equipment such as fire extinguishers and other fire extinguishers within Party B’s construction area乙方施工区域临时移动消防设备，例如灭火器及其它消防仪器 |  | √
10.2 | Firefighting responsibility消防责任 |  | √
10.3 | Construction site safety civilization construction and environmental protection facilities施工现场安全文明施工和环保设施 |  | √
11 | Labor protection and safety劳动保护及安全
11.1 | Safety protective products (such as hard hats, work clothes, labor protection shoes, safety belts, goggles, etc.) are configured by Party B according to Party A’s requirement or by Party A with compensation安全防护用品（如安全帽、工作服、劳保鞋、安全带、护眼罩等）乙方按甲方要求配置或甲方有偿统一配置。 |  | √
11.2 | safety in Party B’s construction area乙方施工区域安全 |  | √
11.3 | Party B's office, workshop, construction site and other facilities乙方办公室、班房、施工地点及其它设施。 |  | √
12 | Licenses and permits 许可证办理
12.1 | Party B shall fill up the information templates provided by Party A ；Party A is responsible for purchasing and making access cards or boichemic scan for site entrance(where necessary)现场出入许可证，乙方按照加饭提供信息模板填报，甲方负责购买制作门禁卡或扫描进入 | √ | √
12.2 | Other relevant permits (if required / applicable) shall be obtained during construction其它施工过程中所须取得的相关许可证件等（如需要） |  | √
13 | insurance保险
13.1 | General liability insurance (personal injury and property loss) for Party B’s staff or Party B’s subcontractor乙方人员或其下游分包单位人员的一般责任保险（人身伤害及财产损失） |  | √
13.2 | Party B shall indemnify the workers compensation insurance, injury insurance and accident insurance.乙方人员劳工赔偿保险, 工伤保险，意外险 |  | √
13.3 | Employer liability insurance of Party B乙方雇主责任保险 |  | √
13.4 | insurance/comprehensive liability insurance for Party B’s motor vehicle乙方车船保险 /综合汽车责任险 |  | √
13.5 | the industrial machinery insurance for Party B’s machinery and tools乙方机械、工机具保险 |  | √
14 | Taxes and duties税收及关税
14.1 | Income tax of Party B (if applicable)乙方企业所得税 |  | √
14.2 | Value Added Tax related to this subcontract.本合同增值税 | √
14.3 | The individual income tax of Party B’s staff乙方个人所得税 |  | √
14.4 | Training costs for Party B’s staff乙方人员相关培训费 |  | √
14.5 | Custom Duty（if any)关税（若有）
14.5.1 | Party A shall be responsible for 5% Custom Duty payable for Pre-fabrication of materials and equipment supplied by Party A .甲方负责甲供应材料及设备的关税。 | √
14.5.2 | Party B shall be responsible for all related taxes, VAT, Import Custom duty, Custom Duty of pre-fabrication for the materials and equipment procured by Party B . 乙方供应材料及设备，及所有相关的税,包括但不限于关税及预制关税及进口增值税。 |  | √
14.6 | Stamp duty of Party B (if any) 乙方的印花税(如有) |  | √
14.7 | Other related taxes related to the work of Party B 其它因乙方工作所涉及的相关税收 |  | √
14.8 | Export agency fees, transportation, load and unload, rehanding within Party B's supply 乙方供应范围内的出口代理费，运费，装卸车费,转运费等 |  | √
15 | Accommodation, transportation, food and visa 住宿，交通，伙食和签证
15.1 | The wages of Party B's staff (including wages, overtime, insurance, income tax, allowances, etc.) and other expenses incurred by the government 乙方员工的工资费用（包括工资，加班费、保险费，所得税，津贴等）和其余由政府规定的费用。 |  | √
15.2 | travel charges, board and lodging, food,etc.乙方人员差旅费、住宿、用餐等 |  | √
15.3 | The cost of transportation for the project of Party B乙方人员项目所在地交通费用 |  | √
15.4 | Party B shall, in accordance with the provisions of Party A, provide the construction personnel with labor protection supplies and equipment.乙方必须按照甲方规定对其施工人员配备劳保用品和用具 |  | √
15.5 | 乙方人员办公用品及办公室设施、住宿设施、食堂、饮水及饮水设施、卫生设施、消毒液及消毒工作等。 All the office supplies and facilities, accommodation, kitchen,potable water and facilities, cleaning/sanitation supplies, disinfection and such disinfection work, etc. |  | √
16 | Inspection and related document验收及资料
16.1 | Equipped with the relevant acceptance equipment and through the relevant requirements and testing. 配备相关的验收设备并通过相关要求及检测等。 |  | √
16.2 | 4 sets hard copy of Formal acceptance and completion of documents and 1 set of soft copy(the final quantities of the copies shall be confirmed by Party A). 正式验收和竣工资料等文件4份纸质版及一份电子版(根据甲方最终要求确定）。 |  | √
17 | Acceptance and document 验收及资料
17.1 | Equipped with the relevant acceptance equipment and pass through the relevant requirements and tests. 配备相关的验收设备并通过相关要求及检测等。 |  | √
17.2 | The formal acceptance and completion documents shall be submitted in paper and electronic versions as required by Party A.正式验收和竣工资料等文件按甲方要求提交纸质版和电子版。 |  | √
18 | HSE management安健环管理
18.1 | To realize uniform management on project site, all of Party B’s signboards not be hanged out until get the approval of Party A. 为实现规范化管理，乙方标识标牌需报甲方报批后方可使用。 |  | √
18.2 | The party B is required to provide on-site toilets and waste disposal at the construction site for their workscope. Local community services will be given priority. 乙方需提供现场工地厕所，优先考虑当地社区提供服务 |  | √
19 | Design(preliminary design, calculation sheet, specification, construction drawing, shop drawing,as-built drawing)设计（详设，计算书，技术规范书，施工图，预制图，竣工图）仅提供电子版 | √
20 | Site office and warehouse of Party B乙方现场办公室及仓库 |  | √
21 | Material supply and installation (the Subcontractor shall revise it as per their design experience), including materials sample survey (if any),材料供应及安装（分包商需根据设计经验修订）包括材料样品研究 |  | √
22 | Civil work土建工作 |  | √
23 | Supply and Installation of all equipments and materials所有设备及材料的供应及安装 |  | √
25 | Testing and Commissioning实验和调试 |  | √
26 | Training（not applicable)培训(不适用） |  | √
27 | Provide the spare parts and especial tools（if any)提供备件及特殊工具（若有） | √
29 | Permits for all the activities所有活动的许可 |  | √
31 | Supply and installation of temporary label and permanent label临时标牌和永久标牌的供应及安装 |  | √
32 | Site clearing场地清理
32.1 | Keep the construction site clean during the construction period, and clean up the site after the construction is completed.施工期间保持施工场地清洁，施工完成后清理场地 |  | √
32.1 | Recyclable leftover materials or packaging, cable reels, etc., shall be cleared by Party B to the location designated by Party A可回收的剩余材料或包装等，需要乙方清理至甲方指定位置 |  | √
33 | Protection of equipments, materials and construction machines设备，材料及施工机械的保护 |  | √
NOTE.注意 This appendix is written in both English and Chinese, should any conflict and discrepancy rise, English shall prevail. 本文由中英双语编制，若有任何冲突和歧义，以英文为准。